## Gantt Chart w % Complete
Build better gantt charts with TeamGantt for FREE!
* = an automatically calculated cell
| TASK NAME | START DATE | DAY OF THE PROJECT* | END DATE | DURATION* (WORK DAYS) | DAYS COMPLETE* | DAYS REMAINING* | PERCENT COMPLETE
Kick-off
| Team forming | 2019-02-05 | 0 | 2019-02-05 | 1 | 1 | 0 | 100%
| Research algorithms | 2019-02-06 | 1 | 2019-02-20 | 15 | 15 | 0 | 100%
| Preparation to meet tutor | 2019-02-13 | 8 | 2019-02-13 | 1 | 1 | 0 | 100%
Initial phase
| Create project plan for Iteration 1 | 2019-02-14 | 9 | 2019-02-19 | 6 | 6 | 0 | 100%
| Update project plan and URS | 2019-02-21 | 16 | 2019-03-14 | 22 | 22 | 0 | 100%
| Create work division report | 2019-02-14 | 9 | 2019-03-12 | 27 | 27 | 0 | 100%
| Create work plan for Iteration 1 | 2019-02-21 | 16 | 2019-03-12 | 20 | 20 | 0 | 100%
Iteration 1
| Present and discuss URS | 2019-03-13 | 36 | 2019-03-13 | 1 | 1 | 0 | 100%
| Work on the PoC | 2019-03-14 | 37 | 2019-04-14 | 32 | 5 | 27 | 20%
| Create work plan for Iteration 2 | 2019-03-21 | 44 | 2019-04-14 | 25 | 0 | 25 | 0%
| Update work division report | 2019-03-14 | 37 | 2019-04-14 | 32 | 5 | 27 | 10%
| Continue researching algorithms | 2019-03-14 | 37 | 2019-04-14 | 32 | 5 | 27 | 20%
| Create UML Class diagrams | 2019-04-01 | 55 | 2019-04-14 | 14 | 0 | 14 | 0%
Calibration
| Prepare for presentation | 2019-04-14 | 68 | 2019-04-21 | 8 | 0 | 8 | 0%
Formulas:
DURATION* (WORK DAYS) = DAYS([END DATE],[START DATE])+1
DAYS COMPLETE* = IF(DAYS(TODAY(),[START DATE])>[DURATION* (WORK DAYS)],[DURATION* (WORK DAYS)],IF(DAYS(TODAY(),[START DATE])<=0,0,DAYS(TODAY(),[START DATE])))

## Basic Gantt Chart
GANTT CHART TEMPLATE
* = an automatically calculated cell
| TASK NAME | START DATE | END DATE | START ON DAY* | DURATION* (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
Kick-off
| Team forming | 2018-01-05 | 2018-01-08 | 0 | 4 | Nathan | 100%
| Research algorithms | 2018-01-08 | 2018-01-11 | 3 | 4 | Meredith | 100%
| Preparation to meet client | 2018-01-11 | 2018-01-16 | 6 | 6 | Brandon | 100%
Initial phase
| Create project plan for Iteration 1 | 2018-01-09 | 2018-01-12 | 4 | 4 | Nathan | 100%
| Update Project Plan and URS | 2018-01-12 | 2018-01-19 | 7 | 8 | Meredith | 80%
| Preparation to meet client | 2018-01-17 | 2018-01-19 | 12 | 3 | Brandon | 60%
| Create work division report | 2018-01-22 | 2018-01-26 | 17 | 5 | Michael | 100%
| Create work plan for Iteration 1 | 2018-01-22 | 2018-01-26 | 17 | 5 | Michael | 140%
Iteration 1
| Plan Agenda for Meeting | 2018-01-15 | 2018-01-19 | 10 | 5 | Nathan | 100%
| Reserve Room | 2018-01-22 | 2018-01-23 | 17 | 2 | Meredith | 80%
| Finalize Presentation | 2018-01-22 | 2018-01-26 | 17 | 5 | Brandon | 60%
| Approve Presentation | 2018-01-26 | 2018-01-29 | 21 | 4 | Michael | 40%
| Create Invitations | 2018-01-22 | 2018-01-25 | 17 | 4 | Rachel | 20%
Iteration 4
| Rewrite Online Calculator | 2018-01-15 | 2018-01-24 | 10 | 10 | Nathan | 100%
| Code Review Calculator | 2018-01-25 | 2018-01-30 | 20 | 6 | Meredith | 80%
| Update Messaging | 2018-01-24 | 2018-01-30 | 19 | 7 | Michael | 60%
| Publish Calculator | 2018-01-30 | 2018-01-31 | 25 | 2 | Rachel | 0%
Formulas:
DURATION* (WORK DAYS) = DATEDIF([START DATE],[END DATE],"d")+1

## Manual Chart
GANTT CHART TEMPLATE
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
First Sample Project
| Write Landing Page Copy | 2018-01-05 | 2018-01-08 | 2 | Nathan | 100%
|  |  |  | 0 | Meredith | 80% | bar: WEEK 2 M to WEEK 2 T
| Review Landing Page Design | 2018-01-11 | 2018-01-16 | 4 | Brandon | 60% | bar: WEEK 1 F to WEEK 2 Th
| Build Landing Page | 2018-01-14 | 2018-01-19 | 5 | Michael | 40% | bar: WEEK 2 T to WEEK 3 M
| Code Review Landing Page | 2018-01-17 | 2018-01-21 | 3 | Rachel | 20% | bar: WEEK 2 Th to WEEK 3 W
| Promote Landing Page | 2018-01-20 | 2018-01-23 | 2 | Annie | 10% | bar: WEEK 3 T to WEEK 3 Th
Second Sample Project
| Write Promotional Email | 2018-02-05 | 2018-02-08 | 4 | Nathan | 100%
| Design Promotional Email | 2018-02-08 | 2018-02-13 | 4 | Meredith | 80%
| Send Promotional Email to Contacts | 2018-02-11 | 2018-02-16 | 5 | Michael | 60%
| Analyze Results of Email Campagin | 2018-02-14 | 2018-02-23 | 8 | Annie | 40%
Third Sample Project
| Plan Agenda for Team Meeting | 2018-03-05 | 2018-03-08 | 4 | Rachel | 100%
| Reserve Room and Resources for Meeting | 2018-03-08 | 2018-03-13 | 4 | Michael | 80%
| Finalize Team Presentation | 2018-03-11 | 2018-03-16 | 5 | Brandon | 60%
| Review & Approve Presentation | 2018-03-14 | 2018-03-19 | 4 | Meredith | 40%
| Create Invitations for Meeting | 2018-03-17 | 2018-03-21 | 3 | Annie | 20%
| Setup Room for Meeting | 2018-03-20 | 2018-03-25 | 4 | Nathan | 10%
Fourth Sample Project
| Rewrite Code for Online Calculator | 2018-04-05 | 2018-04-08 | 2 | Nathan | 100%
| Code Review Updated Calculator | 2018-04-08 | 2018-04-10 | 2 | Meredith | 80%
| Update Messaging for Calculator | 2018-04-11 | 2018-04-16 | 4 | Michael | 60%
| Publish New Calculator to Site | 2018-04-14 | 2018-04-18 | 3 | Rachel | 40%
Formulas:
DURATION (WORK DAYS) = NETWORKDAYS([START DATE],[END DATE])